REF.  NO. 757/DoT&CAv                                                         Dated: 23/06/2025

Request for Proposal (RFP)

For

Engagement of Survey Agencies for conducting Surveys for Data on Domestic and Foreign Tourist visitors/visits in Various Destinations/Accommodation Units/Entry-Exit Points in all districts of Sikkim.

GOVERNMENT OF SIKKIM

TOURISM & CIVIL AVIATION DEPARTMENT

- PARYATAN BHAWAN, TADONG

- GANGTOK

- 737102

Supported by the Ministry of Tourism, Government of India

- CONTENT                                                                                                                        PAGE

- Introduction   ………………………………………………………………………………….. 7

2.   Invitation for Proposal ………………………………………………………………………… 8

(1)       Invitation …………………………………………………………………………….. 8

(2)       Important Dates ……………………………………………………..……………….. 9

3    Instructions to the Bidders ……………………………………………………………………   9

(1)     Completeness of Response …………………………………………………………..    9

(2)     Bid Security Declaration (BSD) ……………………………………………………..  10

(3)     RFP Preparation Cost and Related Issues …………………………………………… 10

(4)     Right to Terminate the Process ……………………………………………………… 11

(5)     No Consortium …………………………………………………………………......... 11

(6)     Submission of Responses/Bids …………………………………………………........ 11

(7)     Proposal Submitted ………………………………………………………………….. 11

(8)     Proposal Validity and Evaluation …………………………………………………… 12

(9)     Procedure for Submission of Bids …………………………………………………..  13

(10)   Bid Content ………………………………………………………………………….  13

(11)   Bidder Qualification …………………………………………………………….......   13

(12)   Period of Validity of Bids ………………………………………………………......   14

(13)   Period of Validity of Work Order/Engagement ………………………………...….   14

(14)   Performance Guarantee …………………………………………………………….   14

(15)   Non-Compliance and Blacklisting ………………………………………………....    15

(16)   Dispute Resolution and Jurisdiction ……………………………………………….    15

(17)   Force Majeure ………………………………………………………………………  15

(18)   General Conditions …………………………………………………………………  15

(19)   Cost of Tender Form  …………………………………………………………..…..   16

4.      Scope of Work, Coverage and Detailed Requirements …………………………………...  16

(1)     Overview …………………………………………………………………………… 16

(2)     Survey Methodology ………………………………………………………………... 17

(3)     IT Requirements ……………………………………………………………………..  21

(4)     Training of Trainers (TOT) and Knowledge Transfer ………………………………. 22

(5)     Cost Implications for Trainings to Surveyors & Supervisors ……………………….  22

(6)    The Coverage in the State of Sikkim ………………………………………………..   22

(7)     Work Load Assessment ………………………………………………………….…   23

(8)      Manpower Requirement Assessment ………………………………………………   23

5.      Eligibility, Qualification and Evaluation Criteria for Financial Bid ……………………… 24

(1) Selection Criteria for Financial Bid Evaluation ………………………………………... 24

(2) Financial Bid Opening Process ………………………………………………………… 24

(3) Financial Bid Evaluation Criteria …………………………………………………….... 24

(4) Selection Criteria ………………………………………………………………………. 25

6.     Award of Work Order (W.O) Letter of Engagement of Survey …………………………... 25     Agency in the State

7.     Deliverables………………………………………………………………………………… 26

7(1)       Deliverables and Time Frame …………………………………………………….. 26

7(2)       Schedule of Payment ……………………………………………………………… 30

8.        General Conditions of the Contract (GCC) ……………………………………………… 34

(1)      Relationship between the Parties ………………………………………………… 34

(2)      Location ………………………………………………………………………….. 34

(3)      Taxes and Duties ………………………………………………………………… 34

(4)      Commencement, Completion, Modification and Termination of contract………. 34

(5)       Force Majeure …………………………………………………………………..  35

(6)       Withholding of Payment ……………………………………………………….   37

(7)        Termination by the Department ……………………………………………….   37

(8)       Termination by the Bidder ….. …………………………………………………. 38

(9)        Cessation of Rights and Obligations …………………………………………...  38

(10)       Cessation of Services ………………………………………………………….  39

(11)      Payment upon Termination …………………………………………………….. 39

(12)       Disputes about Events of Termination ………………………………………… 39

9.   Obligations of the Bidder ………………………………………………………………. 40

(1)        Standard of Performance ………………………………………………………. 40

(2)        Conflict of Interest …………………………………………………………….. 40

(3)        Confidentiality ………………………………………………………………… 41

(4)        Accounting …………………………………………………………………….. 41

(5)        Bidders Action Requiring ……………………………………………………..  41

(6)        Deliverables ……………………………………………………………………. 42

(7)        Documents prepared by Bidder to be the Property of  the Department…………42

10.   Bidders Personnel …………………………………………………………………….. 42

(1)           General ………………………………………………………………………. 42

(2)           Description of Personnel …………………………………………………….. 42

11.     Obligations of the Department…………………………………….. ………………..  42

(1)           Assistance and Exemptions ………………………………………………….. 42

(2)           Payments …………………………………………………………………...... 42

(3)           Office Space and Other Facilities …………………………………………… 43

12.         Payments to the Bidder …………………………………………………………… 43

(1)       Total Cost of the Services ………………………………………………….…... 43

(2)       Currency of Payment …………………………………………………………… 43

(3)       Terms of Payment ……………………………………………………………… 43

(4)       Final Payment …………………………………………………………………..  44

13.        Fairness and Good Faith ……………………………………………………………45

(1)      Good Faith ………………………………………………………………………  45

(2)      Operation of the Contract ……………………………………………………….  45

14.        Settlement of Disputes …………………………………………………………….. 45

(1)       Amicable Settlement …………………………………………………………… 45

15.       Penalty Clause ……………………………………………………………………… 46

16.        Conflict of Interest ………………………………………………………………… 47

17.       Conflicting Activities ………………………………………………………………. 47

18.       Association of Sub-bidders ………………………………………………………… 47

19.       Confidentiality ……………………………………………………………………... 47

20.       Contract Price ………………………………………………………………………. 48

21.       Transfer of Contract ………………………………………………………………    48

22.       Time and Cost Overrun due to Pandemic ………………………………………….. 48

23.       Change Orders ………………………………………………………………………48

24.       Tender Summary …………………………………………………………………… 49

ANNEXURE “A”.……………………………………………………………………….…. 50

(List of Districts to be covered in Sikkim)

ANNEXURE “B” ………………………………………………………………………….. 51

(List of Destinations District wise)

ANNEXURE “C” ………………………………………………………………………….. 53

(District wise List of Accommodation Units)

ANNEXURE “D” ………………………………………………………………………….. 54

(List of Exit Points (Air/Water/Road/Rail) District wise

ANNEXURE “E” …………………………………………………………………………..  56

(Cost and Workload Estimation Sheet)

Form Tech 1 – Financial Bid Form …………………………………………………………59

Form Tech 2 – Declaration (on the Letter Head of the Bidder) ……………………………  60

Form Tech 3 – Bid Security Declaration Form ……………………………………………..61

Form Tech 4 – List of Surveyors …………………………………………………………..  62

Form Tech 5 – Banking Details Performa of the Bidder …………………………………... 63

ANNEXURE 1 – Tourism Survey Methodology ………………………………………….. 64

ANNEXURE 2 – Tender Form …………………………………………………………….. 65

- Introduction:

Tourism and Civil Aviation Department, Government of Sikkim (hereinafter referred to as the “Department”) under the direction of the Ministry of Tourism Government of India, intends to carry out the Survey for Data on “Domestic and Foreign Tourist Visitors/Visits” in Various Tourist Destinations/Accommodation Units/Entry-Exit Points including Airport in all the six districts of the state namely:

- Mangan

- Gyalshing

- Namchi

- Gangtok

- Soreng

- Pakyong

The survey intends to capture the details of both Domestic and Foreign Tourist Visits in the State as per the latest and new guidelines/methodology supplied by the Ministry of Tourism, Government of India.

The survey shall cover all the Entry/Exit Points including bus stand or taxi stand and airport of the State. It shall also cover all the prominent tourist destinations. The survey shall also cover and collect data from accommodation units, profile of the visitors, purpose of visit, length of stay, visitors’ preferences, expenditure and hotels occupancy from all the six districts.

The survey shall be for a period of 13(thirteen) months (Phase One – One month and Phase Two – Twelve Months) starting from the launching of survey.

## 2.  Invitation for Proposal:

(    1             )                                                              Invitation

- The Department intends to engage Survey Agency from the list Empanelled with MoT vide RFE No 10(1) 2018-MRD dated 17th August 2022 for conducting the tourism survey at Destinations, District Level & State/UT Level across the State/ UT.

(b) Tourism and Civil Aviation Department, Government of Sikkim invites Proposal from empanelled agencies to select a preferred agency who is capable of conducting the tourism survey at Destinations, District level in the State of Sikkim. List of Districts to be covered, List of Destinations, District wise List of Accommodation Units, and List of Exit Points is attached at Annexure A, B, C and D respectively.

(c)	Respondents to this RFP (also referred to as “bidders”) are expected to follow the detailed instructions provided herein carefully. Failure to follow the format as instructed may result in disqualification of the proposal. Bidders will be further shortlisted after an evaluation of responses/ proposals received and will be subjected to final negotiations as necessary.

- This RFP will be published in the official website of the Department, at www.sikkimtourism.gov.in . The Bidders are required to submit hard copies of their proposals within the stipulated times as mentioned in clause 2 addressed to the Additional Secretary, Tourism and Civil Aviation Department, Government of Sikkim, Paryatan Bhawan, Metro Point Tadong, Gangtok-737102. For any clarification on the RFP, please contact through email at ad.marketresearch.sikkimtourism@gmail.com.

- The successful bidder for tourism survey agency shall work under directions of the Department. After engagement of the successful Agency by the Department, a training of trainers (ToT) on Survey Methodology of conducting the surveys will be scheduled by National Productivity Council (NPC) for the state level supervisors of the Survey Agencies to develop Master Trainers (MTs). The NPC will conduct the above mentioned trainings for providing an understanding of methodology to be followed by engaged agencies and their respective supervisors for execution of state tourism survey through workshops at regional level to develop MTs. Further it will be responsibility of the engaged Survey Agency to impart trainings through these MT to field surveyors and supervisors at no cost of the Department, and ensure the quality of Tourism Survey.

- For speeding up the data entry, compilation, analysis & reporting on monthly basis, a mobile app will be provided to the surveyors. The field surveyors are required to use the mobile app to fill, validate and send the data to Dashboard of MoT.

- The Department reserves the right to reject any or all of the responses to this RFP without assigning any reason. The Department takes no responsibility for delay, loss or non-receipt of response to RFP.

## (2)       Important Dates

| Sl. No. | Particular | Timelines |
| --- | --- | --- |
| 1 | Start date of publishing of RFP document on the official website www.sikkimtourism.gov.in | 23/06/2025 |
| 2 | Last date and time for submission of bids | 18/07/2025 |
| 3 | Date of opening of Financial bids | 23/07/2025 |
| 4 | Release of ranking of Bidders | 29/07/2025 |
| 5 | Award of Work Order & signing of contract | 18/08/2025 |

*Days mentioned are (Calendar Days)

## Instructions to the Bidders

## Completeness of Response:

(a) Agency is required to study all instructions, forms, requirements and other information in the RFP documents carefully. Submission of the bid shall be deemed to have been done after careful study and examination of the RFP document with full understanding of its implications. The response to this RFP should be full and complete in all respects. Failure to furnish all information required by the RFP documents or submission of a proposal not substantially responsive to this document will be at the Bidder's risk and may result in rejection of its Proposal. The declaration by bidder will be submitted as per Form Tech-2. It should be ensured that various formats mentioned in this RFP should be adhered to and no changes in the format should be done. The document should be page numbered, must contain the list of contents with page numbers and each page shall be initialed by the Authorized Representative of the bidder. RFP submitted by the bidder should be   concise and contain only relevant information as required.

## Bid Security Declaration (BSD):

## Bidders should submit along with their Bids, Bid Security Declaration (BSD). The bid/ proposal submitted without BSD, mentioned above, will be summarily rejected.

    - BSD should be submitted as per Formtech-3 of RFP.

    - The Bidder shall be suspended for a period of 3 Years/ duration:

(i)  if a bidder withdraws or modifies its bid during the period of bid validity.

- in case of a successful Bidder, if the Bidder fails to sign the Agreement in accordance with the terms and conditions (including timelines for execution of the Agreement) of this RFP.

- during the Bid process, if a Bidder indulges in any act as would jeopardize or unnecessarily delay the process of bid evaluation and finalization;

    - The decision of the Department regarding selection of agency and award of work shall be final and binding on the Bidder and shall not be called upon in question under any circumstances.

## RFP Preparation Costs and related issues:

- The agency is responsible for all costs incurred in connection with participation in this process, including, but not limited to, costs incurred in conduct of informative and other diligence activities, participation in meetings/ discussions/ presentations, preparation of proposal, in providing any additional information required by Department to facilitate the evaluation process. The Department will in no case be responsible or liable for those costs, regardless of the conduct or outcome of     the bidding process.

- This RFP does not commit Department to award the Work Order or to engage in negotiations. Further, no reimbursable cost may be incurred in anticipation of award or for preparing this RFP.

## Right to Terminate the Process:

(i)  The Department may terminate the RFP process at any time and without assigning any reason thereof. The Department makes no commitments, express or implied that this process will result in a business transaction with anyone. This RFP does not constitute an offer by the Department.

(ii)   The bidder's participation in this process may or may not result in short listing the bidder.

## No Consortium:

- No Consortium will be allowed. The bidder must meet all the eligibility criteria by itself.

## Submission of Responses or Bids:

Proposal must be submitted in hard copies or through Speed Post addressing the Competent Authority as mentioned in the item (d) of Sub- clause 2(1) of Clause 2. The Bidder shall submit all the required documents as mentioned in the FORM TECH (1 to 5) including various templates. Proposal submitted by the bidder should be concise and contain only relevant information as required.

## Proposal submitted:

    - Proposal submitted will be opened by a bid opening committee as per the schedule as mentioned in Sub-clause (2) of clause 2, constituted by the Department, in the presence of such agency or their representatives who may wish to be present at the time of opening.

    - The representatives of the agency are advised to carry the “Letter of Empanelment with MoT”, the identity card or a letter of authority from the participating firms to identify them as bonafide for attending the opening of the proposal.

## Proposal Validity and Evaluation:

    - The offer submitted by the bidder should be valid for minimum period of 180 days from the date of submission of Proposal as per sub-clause (2) of clause 2. Initial Bid scrutiny will be held and incomplete details as given below will be treated as non-responsive, if Proposals;

- are not submitted in as specified in the RFP document;

- received without a copy of “Letter of Empanelment with MoT” ;

- received without the Letter of Authorization;

- received without BSD (Bid Security Declaration);

- are found with suppression of details with incomplete information, subjective, conditional offers and partial offers submitted;

- submitted without the documents/ information requested in the FORM TECH – (1 to 5);

- have non compliance of any of the clauses stipulated in the RFP;

- with lesser validity period;

- are not submitted on or before the last date of submission and within the time limit (As specified by the Tourism and Civil Aviation Department, Govt. of Sikkim;

    - All responsive Bids will be considered for further processing by the Department. All eligible bids will be considered for further evaluation by the Evaluation Committee (ECE) according to the evaluation process defined in this RFP document. After evaluation of bids by ECE as per RFP, a ranking of agencies will be prepared and submitted for perusal and approval at Tourism and Civil Aviation Department, Govt. of Sikkim.

(c)  Work Order will be issued to agency by the Department to the successful Bidder. However, the Department reserves the right to accept or reject any proposal, and to annul the bidding process / Public procurement process and reject all proposals at any time prior to award of Work Order, without thereby incurring any liability to the affected bidder or bidders or any obligation to inform the affected bidder or bidders of the grounds for Department action.

## Procedure for Submission of Bids:

(a) This document is a Financial Bid.

- This RFP Document has been uploaded on the website of the Tourism and Civil Aviation Department, Govt. of Sikkim at www.sikkimtourism.gov.in.

- Bidders are advised to study the Bid document carefully. Submission of bids shall be deemed to have been done after careful study and examination of the bid document with full understanding of its implications. Bid offers prepared in accordance with the procedures enumerated in clause 3 should be submitted not later than the last date laid down under sub-clause (2) of clause 2 under “Important Dates” in hard copies or through Speed Post addressing the Competent Authority as mentioned in item (d) of clause 2 (1).

## Bid Contents:

- In the absence of any information, as requested above, a bid may be considered   incomplete and summarily rejected.

- The Bidder shall prepare the bid based on details provided in the Bid documents. Bidder shall carry out the study of the bill of material in accordance with the requirements of the Bid document and it shall be the responsibility of the Bidder to fully meet all the requirements of the Bid document.

## Bidder Qualification:

(a) The "Bidder" as used in the Bid documents shall mean the one who participate in the bid process. The Bidder may be either the Constituted Attorney of the agency or the Principal Officer or his duly Authorized Representative, in which case he/she shall submit a certificate of authority. All certificates and documents (including any clarifications sought and any subsequent correspondences) received hereby, shall, be furnished and signed by the Bidder.

(b) It is further clarified that the individual signing the Bid or other documents in connection with the Bid must certify whether he/she signs as:

(i)   Constituted Attorney of the agency;

### OR

(ii) The Principal Officer or his duly Authorized Representative of the agency, in which case he/she shall submit a certificate of authority on behalf of the agency/organization;

- The Bidder shall sign its Bids with the exact name of the agency/ organization to whom the contract is to be issued.

- The Bidder shall clearly indicate their legal constitution and the person signing the Bids shall state his capacity and also source of his ability to bind the Bidder.

- The Department may out rightly reject any bid not supported by adequate proof of the signatory’s authority.

## Period of Validity of Bids:

- Bids shall remain valid for 180 days after the date of opening of Financial Bids prescribed by the Department. A bid valid for a shorter period may be rejected by the Department as non-responsive.

- In exceptional circumstances, the Department may ask the Bidder to extend the validity of the Bid. However, a Bidder will not be permitted to modify its bid.

## Period of Validity of Work Order/Engagement

The engagement of the agency will be for a period of 24 months from date of issue of Letter of Issue of Work Order subject to performance review on annual basis.

## Performance Guarantee:

(a) Performance Guarantee @ 3% of offered amount of tender to be deposited by a successful bidder before issuing a work order by Department, Government of Sikkim

(b) The Performance Guarantee may be in the form of Demand Draft / Banker’s Cheque / Bank Receipts in favour of Senior Accounts Officer - cum-D&DO, Tourism and Civil Aviation Department, Government of Sikkim.

(c) The Performance Guarantee shall be payable to the Purchaser Department as a compensation for any loss resulting from the Bidder’s failure to complete its obligations under the contract.

## Non Compliance and Blacklisting

(a)   The Department reserves the right to engage the Empanelled Agency for conducting Tourism Survey in various districts of Sikkim.

(b)  Non-compliance, unsatisfactory performances in this regards without a valid reason may lead to penalty or Blacklisting of the agency as deemed fit by the Department.

## (16)       Dispute Resolution and Jurisdiction:

Any dispute to be resolved amicably by the executants of the RFP. Otherwise, the dispute will be referred to an ’Arbitration’ under the Arbitration and Conciliation Act 1996 to be appointed with the consent of both the parties. The decision of the Arbitration will be final and binding on both the parties. As regards the matter when there is no arbitration agreement, the dispute, is to be adjudicated by a civil court at the state level. Apart from Dispute Resolution, the factor of ‘Force Majeure’ to be considered and no party should be blamed for the same.

## Force Majeure:

This RFP is subject to force majeure situations. It shall be subject to inabilities based on circumstances beyond the control and power of contracting parties, such as but not limited to civil commotion, riots, war, pandemics, Acts of God, hacking, unauthorized access, spam etc., which may result in the prevention of performance by a party.

## General Conditions:

- While every effort has been made to provide comprehensive and accurate background information, requirements, and specifications, bidders must form their own conclusions about the requirements.

    - all information supplied by bidders may be treated as contractually binding on the Agency, on successful award of Work Order by the Department based on this RFP.

    - the Department reserve the right to deploy the empanelled agency to any of the locations across the State in the region.

    - the engagement of Surveyor Agency will be reviewed monthly/

Quarterly / Annually and extended subject to satisfactory performance.

    - the criteria for performance evaluation is directly linked to the deliverables of the contents of the RFP. Refer clause-7: Deliverables and Time Frame.

- Cost of Tender Form:

Tender form is enclosed in ANNEXURE-2 of this RFP. The cost of tender form should be deposited towards the Department for Rs. 5000/- (Rupees Five Thousand) (Non-Refundable) under the Major Head 1452/TD, 800-Other Receipts.

Payment of this shall be made either in Banker’s Cheque or Bank Receipt (BR) in the State Bank of Sikkim in favour of Accounts Officer-cum-D&DO, Tourism and Civil Aviation Department, Government of Sikkim before the submission of Financial Bid.

# Scope of Work, Coverage and detailed requirements

## Overview:

(a) Ministry of Tourism has taken up an initiative for implementation of “Standard Tourism Survey Methodology” across all districts of the state. One of the main objectives is to estimate the data on domestic tourist visitors and foreign tourist visitors, their profiling, purpose of   visit, visitor’s preferences, length of stay, expenditure, hotels occupancy etc.

(b) the data shall be collected every month at following three points on sample basis;

(i)    major tourist destinations of the districts;

(ii)  departure points of the district i.e. Bus terminals, Taxi Stands and Airport;

- accommodation units of the districts;

(c)  the data from all three sources will be processed together based on set algorithm to arrive at the final outcome. The data shall be collected for all districts of the state. The detailed tourism survey methodology is given at Annexure-1;

- for speeding up the data entry, compilation, analysis and reporting on monthly basis, a mobile app will be provided to the surveyors;

- the survey shall be used to obtain the month-wise information for each  district of Sikkim.

## (2)  Survey Methodology:

The methodology comprises of 2 phases. First, a preliminary phase of 1 month and second, a main phase of 12 months. The purpose of conducting Phase I (preliminary phase) is to assess the visitor traffic at different destinations/ exit points of the surveys in order to distribute the sample sizes fixed for main surveys among the destinations / exit points. The main surveys would be conducted in phase II. Further details are given in Annexure-1.

### Phase –I:

The duration of Phase 1 will be One month. Destinations:

The main purpose of conducting Phase I (preliminary phase) is to identify major destinations in the district. Surveys will be conducted covering 14 days of a month. First  day of the month will be considered as the first day of the week.

The days on which survey should be done are as follows:

| Week | Days |
| --- | --- |
| 1 | First 03 days |
| 2 | Last 04 days |
| 3 | First 03 days |
| 4 | Last 04 days |

For ticketed destinations, number of visitors will be available from the number of tickets sold. For Non Ticketed destinations, manual counting of visitors entering the destination will be carried out and data will be punched into Mobile app. For the purpose gates/approaches/points from where most of the visitor/tourist (more than 90%) enter needs to be identified.

### Exit point of district:

Observation of pattern of flow of visitor at departure points of taxi stands, bus terminals, Airport etc. It may also be done through analyzing secondary sources of data.

### Accommodation units:

  - to prepare a comprehensive list of all accommodation units in each district;

  - to undertake accommodation unit census with the help of quarterly  accommodation unit census questionnaire;

### Phase –II:

The duration of Phase 2 will be twelve months

In the main phase, the following exercises / surveys / assessments would be carried out:

- in case of ticketed destinations, the number of visits has to be taken from the record of sales of tickets;

- in case of non – ticketed destinations, assessment of the total number of visits has to be made through manual counting similar to Phase 1;

- an investigator needs to be deployed at each of the entry points of the destinations in order to manually count the number of leisure visits to the destination on the selected days/dates;

- important tourism destination will be positively covered. Information about important festivals, fairs, religious events, MICE events, events organized by the Government at the selected tourist destinations will be collected in advance for 12-month period. If the important tourist event at the selected tourist destination falls outside the selected week and dates, the nearest week/ dates will be substituted by the week/ dates of the special event;

(e)  Time Slot should be specific to the destination and should cover:

- the entire duration during which entry is permitted in case of ticketed/ gated destinations;

(ii) the duration in which nearly all the visitors visits in case of a non-ticketed / unrated destinations.

At Destinations: The destinations for which the cumulative count of visits is more than 90% of the total number of visits in the district will be considered as major destinations to be surveyed in the Phase II or the main phase. The survey will be conducted during all the 12 months of the year at each selected destination carried out as per following dates (7 Days  per month):

| Month | Weeks | Days of weeks | Dates of the month |
| --- | --- | --- | --- |
| First | First and Third | 1st week: 1-3 days 3rd week: 4- 7 days | 1, 2, 3,18,19, 20, 21 |
| Second | Second and Fourth | 2nd week: 1-3 days 4th week: 4- 7 days | 8, 9, 10, 25, 26, 27, 28 |
| Third | First and Fourth | 1st week: 1-3 days 4th week: 4- 7 days | 1, 2, 3, 25, 26, 27, 28 |
| Fourth | Second and Third | 2nd week: 1-3 days 3rd week: 4- 7 days | 8, 9,10,18,19, 20, 21 |
| Fifth | First and Second | 1st week: 1-3 days 2nd week: 4- 7 days | 1, 2, 3, 11, 12, 13, 14 |
| Sixth | Third and Fourth | 3rd week: 1-3 days 4th week: 4- 7 days | 15, 16, 17, 25, 26, 27, 28 |
| Seventh to Twelve | Above pattern will be repeated |  |  |

The date and week on which important tourism event is scheduled to take place at the selected tourist destination will be positively covered. The data will be uploaded on a daily basis.

- At Departure point of district: The survey of visitors at all exit points of district (as identified in the phase – I) at the tourist destinations have to be covered. The 14 days of the month on which this survey should be done are as follows:

| Week | Days |
| --- | --- |
| 1 | First 03 days |
| 2 | Last 04 days |
| 3 | First 03 days |
| 4 | Last 04 days |

- At Survey of Accommodation Units: The census list would form the sampling frame for the monthly survey of accommodation units. The accommodation units listed in Phase I will be grouped in the following categories:

  - Classified hotels

  - Other accommodation units.

(a)  Having more than 20 rooms

(b) Having 10-20 rooms

(c)  Having less than 10 rooms

For the purpose of conducting the Accommodation Survey, all the classified hotels and 10% of the units in each of the categories of other accommodation units will be selected by using circular systematic sampling method. Fresh sample would be selected in each month.

From all the selected accommodation units, the following information about overnight visitors will be collected based on the records:

- Number of checked-in (domestic / foreign)

- Number of room nights spent (domestic / foreign)

- Residency status of the tourists (within the state / within country/ outside country)

- Purpose of their visit etc.

This information has to be collected in the 1st week of every month for the preceding month.

### Following are the particulars of this survey:

Sample size of visitors at district level:

Statistically, a sample of size 384 is required to get estimate of a parameter with a precision of 5% points and 95% level of confidence. For the proposed survey, however, the sample size will be 600 per district per month. For a district if in certain months these much samples are not available, the shortfall should be covered in next months. If a particular district is not important from tourism perspective and the sample size of 600 visitors per month is not likely to be available, then portion of this sample size may be allocated to other districts having larger no. of visitors. This redistribution must be done based on the findings of Phase I of the methodology. At State level, the sample size of 600 x no. of Districts for the survey at Tourist Destinations has to be maintained every month. ii. Distribution of Sample Size among Tourist Destinations: The sample of 600 has to be distributed between the destinations (ticketed and non-ticketed) of the district. This may be done in proportion to the visitors at the destinations as observed in Phase I of the methodology. The sample proportion of domestic as well as foreign visitors is to be decided on the basis of their proportion observed in phase I of the survey Market Research Division, Ministry of Tourism Page 10 of 31 or on the basis of data of ticket sales of previous day in case of destinations with differential tickets.

  - Distribution of Sample Size among Tourist Destinations: The sample of 600 has to be distributed between the destinations (ticketed and non- ticketed) of the district. This may be done in proportion to the visitors at the destinations as observed in Phase I of the methodology. The sample proportion of domestic as well as foreign visitors is to be decided on the basis of their proportion observed in phase I of the survey or on the basis of data of ticket sales of previous day in case of destinations with differential tickets.

  - Time Slots for the survey at a destination: Time slots should be such that they cover the varying visitor traffic pattern at a destination. For example, at some religious places visitors visit the destination in early morning and/ or late evening. Similarly fairs and festivals may draw large number of visitors during late hours in evening. Time slots of the survey at each destination should be devised in a manner so as to capture the variations in visitor inflow.

## (3)  IT Infrastructure requirements:

The field Surveyors are required use the mobile app to be provided by the Ministry of Tourism to fill validate and send the data to Dashboard of MoT. The minimum configuration of Smartphone/ Tab for installation of the mobile app for smooth conduct of Tourism Survey is as follows:

| Configuration Required for Android Mobile/Tab for survey: |  |
| --- | --- |
| Description | Specification |
| Processor make | Qualcomm Snapdragon 865 and 865 Plus |
| Processor Speed | 2.84GHz to 3.1GHz |
| RAM | 4GB |
| Internal storage | 64GB |
| Operating system | Android 7.0 |
| GPS |  |
| Internet Connectivity | Mobile networks/ Wi-Fi |

The smart phones/ tabs available with the surveyors will be upgraded as per the requirement will be upgraded by the agency as per requirement. Each surveyor is required to carry one Smartphone/ Tab of configuration as mentioned above for conducting the field surveys.

## (4) Training of Trainers (ToT) and knowledge transfer:

After engagement of the successful Agency by Tourism and Civil Aviation Department, Govt. of Sikkim, a training of trainers (ToT) on methodology of conducting the surveys will be scheduled for the state level supervisors of the Survey Agencies to develop Master Trainers (MT).

National Productivity Council (NPC) will conduct the above mentioned trainings for providing an understanding of methodology to be followed by empanelled agencies and their respective supervisors for execution of state tourism survey through workshops at regional level to develop MTs.

Further it will be responsibility of the Survey Agency to impart trainings through these MT to field surveyors and ensure the quality of Tourism Survey.

## (5) Cost Implications for trainings to Surveyors and Supervisors:

- The trainings of surveyors and supervisors will be conducted by the empanelled survey agencies at no cost of the Department. The list of manpower may be provided as per Formtech-4.

## The Coverage in the State of Sikkim is given as follows:

- List of Districts to be covered in Sikkim	 Annexure - A

- Lists of Destinations District wise	         Annexure - B

- District wise List of Accommodation Units        Annexure – C

- List of Exit points (Air/Water/Road/ Rail) District wise – Annexure – D

*Note: The lists which have been provided by Tourism and Civil Aviation Department, Govt. of Sikkim in the Annexure – A to D are only for reference purpose and need to be checked and re-verified by the surveyor of the Empanelled Agency for authentication.

## Work Load Assessment:

- The Agency may estimate the Workload as per the given template to understand the quantum of work and ensure effective deployment of manpower. Annexure-E “Cost Estimation Sheet”.

## Manpower Requirement Assessment:

(a) The Agency may estimate the Manpower requirement as per the given template to understand the quantum of field work is for 13 months only and ensure effective deployment of manpower. However, it may be noted that the maximum engagement period of agency will be up to 24 months only.

### Phase 1- Work Content for 1 Month

| S No. | Activity | Manpower Required |
| --- | --- | --- |
| 1 | Listing of tourist accommodation units (from administrative records) to prepare the sampling frame of accommodation units |  |
| 2 | Counting of visitors at all non-ticketed destinations throughout the normal time of entry for 14 prescribed days using mobile application |  |
| 3 | Collection of number of tickets sold from all ticketed destinations for prescribed 14 days of the month |  |
| 4 | Collection of number of tourists/visitors exit through all exit points (to study the flow of exit of visitors) |  |

Phase 2- Work content for 12 Month (1 Year Only)

| S. No. | Activity | Manpower Required |
| --- | --- | --- |
| 1 | Short Survey at Destination: For the duration of 7 days in a month, 600 samples from the district to be collected at the destinations selected as per the 90% criteria. |  |
| 2 | Accommodation Survey: All the classified hotels and 10% of the units in each of the categories of other accommodation units. Information has to be collected in the 1st week of every month for the preceding month |  |
| 3 | Exit Survey: 14 days exercise in a month to perform the 400 survey’s at the exit points. It is to be done at all the points of a district (railway stations, bus-stations, air-ports, and sea-ports) |  |

## 5. Eligibility, Qualification and Evaluation Criteria for Financial Bid

### Selection Criteria for Financial Bid Evaluation:

The   bidder   from   empanelled   list   of   MoT   vide   RFE   No 10(1) 2018-MRD dated 17th August 2022 are eligible to participate in the Financial Bid Evaluation.

### Financial Bid Opening Process:

The Financial Bids of the above short listed bidders from the empanelled list of RFE No 10(1) 2018-MRD dated 17th August 2022 will be opened on the prescribed date in the presence of representatives of the bidders. Refer sub-clause (2) of clause 2.

### Financial Bid Evaluation Criteria:

Format for submitting the financial bid/ Quote is given at Formtech –1.

(a) the bidder is required to submit sealed Financial Bid to the Department in a hard copy;

- the Bids will be opened by Evaluation Committee (ECE) for consideration;

(c)  the time for opening of bids has been mentioned in sub-clause (2) of clause 2;

(d) the bidder with the lowest financial bid (L1) will be ranked 1st and will be listed in ascending order of the bids;

(e) only fixed price financial bids will be considered;

(f) any conditional bid may be rejected.

(g) Errors and Rectification: Arithmetical errors will be rectified on the following basis: “If there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected. If there is a discrepancy between words and figures, the amount in words will prevail”.

### Selection Criteria

      - in the event if bids of more than one bidder are ‘tied’, the bidder  securing the highest technical score during empanelment will be  adjudicated as the Best Value Bidder for award of work order;

      - in case of special circumstance where the L1 bidder is not taking the order, the Department may offer the same to next L2 bidder at the price offered by L1 Bidder.

## 6.  Award of Work Order (W.O) Letter for Engagement of Survey Agency in

the state of Sikkim.

### Award Criteria:

The Department will award the Letter of Engagement to the successful bidder who is eligible as per the criteria mentioned in Clause 5 of this RFP.

### Right to Accept Any Proposal and to Reject Any or All Proposal(s):

The Department reserves the right to accept or reject any proposal, and to annul the engagement process/Public procurement process and reject all proposals without thereby incurring any liability to the affected bidder or bidders or any obligation to inform the affected bidder or bidders of the grounds for the Department action.

### Letter of Engagement for the state of Sikkim:

Prior to the expiration of the validity period, Tourism and Civil Aviation Department, Govt. of Sikkim will notify the eligible bidder in writing or by email regarding their engagement for conducting Tourism surveys. In case the engagement process has not been completed within the stipulated period.

### Acceptance Letter:

The Department will require the empanelled bidder to provide an acceptance letter within 7 days from the issue of Letter of Engagement.

### Engagement Period:

Engagement will be valid for a period of 24 months from the date of issue of W.O. however the engagement of Surveyor Agency will be reviewed Monthly/quarterly/annually. In case of satisfactory performance the engagement will be continued till next review but if the performance is found to be unsatisfactory then the Surveyor Agency shall be warned/suspended/ delisted as deemed fit.

## Deliverables

## 7(1) Deliverables and Time Frame

| S No. | Deliverable | Timeframe* |
| --- | --- | --- |
| 1 | Signing of Contract Agreement and Submission of Bid Security Document | Within 1 Week from Selection |
| 2 | Phase -1 Deliverable |  |
| (1) | Listing of tourist accommodation units (from administrative records) to prepare the sampling frame of accommodation units | 1 Month |
| (2) | Listing of tourist destinations (indicating ticketed/non-ticketed from administrative records) to count the number of visitors | 1 Month |
| (3) | Listing of all tourist exit points (from administrative records) to control flow study | 1 Month |
| (4) (a) | Counting of visitors at all non-ticketed destinations throughout the normal time of entry for 14 prescribed days using mobile application | 1 Month |
| (b) | Execution of enumeration of visitors (to get the proportion of domestic/international visitors) for 14 prescribed days in a month | 1 Month |
| (5) | Collection of number of tickets sold from all ticketed destinations for prescribed 14 days of the month | 1 Month |
| (6) | Collection of number of tourists/visitors exit through all exit points (to study the flow of exit of visitors) | 1 Month |
| (7) | Execution of above tasks by selected investigators under the related supervisors | 1 Month |
| 3 | Deployment of Surveyors. The incumbent will be deployed full time for one year in NPC/Ministry of Tourism | 1 Month |
| 4 | Phase-2 Deliverable |  |
| (1) | To conduct Accommodation Census (to be updated information quarterly)to administer accommodation census questionnaire to each accommodation unit and get it duly filled in | Quarterly |
| (2) | To conduct Accommodation Unit Monthly Survey (on 10% distinct accommodation units) to administer accommodation monthly questionnaire to each accommodation unit and get it duly filled in | Per Month |
| (3) | To conduct monthly Short survey at all destination points selected (based on 90% criteria) for phase-2 study of 12 – months to administer tourist destination short survey questionnaire over 600 visitors /visitor-groups, distributed randomly over the selected destinations and the 7 prescribed days of the month for a period of 12 months phase-2 study | Per Month |
| (4) (a) | To get the total number of visitors visited at tourist destination points selected (on 90% criteria) for the 12-months phase-2 study Collection of number of tickets sold from all selected ticketed destinations (on 90% criteria) on 7 prescribed days of the months during the 12 months phase-2 study period | Per Month |
| (4) (b) | To get the total number of visitors visited at tourist destination points selected (on 90% criteria) for the 12-months phase-2 study Counting of the number of visitors taking entry at all entry points of all the selected Non- ticketed destinations (based on 90% criteria) throughout the normal time of entry on 7 prescribed days of the months during the 12- months phase-2 study | Per Month |
| (5) | To conduct monthly Exit survey at all Exit points on 14 prescribed days of the months during the 12-months phase-2 study of 12 – months to administer tourist exit survey questionnaire over 400 visitors /visitor-groups, distributed randomly over all the exit points and the 14 prescribed days of the month for a period of 12 months phase-2 study | Per Month |

## 7(2) Schedule of Payment

| S. No. | Deliverable |  |  | Payment |
| --- | --- | --- | --- | --- |
| Advance Payment = 25% |  |  |  |  |
|  | Phase-1 |  |  |  |
| 1(1) | Destination: 14 days’ exercise in a month to identify the major tourist destinations at ticketed and non-ticketed destinations |  |  | 10% |
| (2) | Exit Point: 14 days’ exercise in a month to observe the Flow of Exit. It is to be observed at all the points of a district (railway stations, bus-Stations, air-ports, and sea-ports……) |  |  |  |
| (3) | Accommodation Units: To make the list of accommodation units |  |  |  |
| 2 | Phase-2 |  |  |  |
| 2(1) | - Short Survey at Destination: For the duration of 7 days in a month, 600 samples from the district to be collected at the destinations selected as Per the 90% criteria. | First year* | Q1 | 10% |
| 2(2) | - Accommodation Survey: All the classified Hotels and 10% of the units in each of the categories of other accommodation units. Information has to be collected in the 1st week of every month for the preceding month |  |  |  |

| 2(3) | - Exit Survey: 14 days exercise in a month to perform the 400 surveys at the exit points. It is to be done at all the points of a district (railway stations, bus- stations, air-ports, and sea- ports……) |  |  |  |
| --- | --- | --- | --- | --- |
| 2(4) | - Short Survey at Destination: For the duration of 7 days in a month, 600 samples from the district to be collected at the destinations selected as Per the 90% criteria. |  | Q2 | 15% |
| 2(5) | - Accommodation Survey: All the classified Hotels and 10% of the units in each of the categories of other accommodation units. Information has to be collected in the 1st week of every month for the preceding month |  |  |  |
| 2(6) | - Exit Survey: 14 days exercise in a month to perform the 400 surveys at the exit points. It is to be done at all the points of a district (railway stations, bus-stations, air‐ports, and sea‐ ports……) |  |  |  |
| 2(7) | - Short Survey at Destination: For the duration of 7 days in a month, 600 samples from the district to be collected at the destinations selected as per the 90% criteria. |  | Q3 | 15% |
| 2(8) | - Exit Survey: 14 days exercise in a month to perform the 400 surveys at the exit points. It is to be done at all the points of a district (railway stations, bus- stations, air-ports, and sea-ports……) |  |  |  |
| 2(9) | - Accommodation Survey: All the classified hotels and 10% of the units in each of the categories of other accommodation units. Information has to be collected in the 1st week of every month for the preceding month. and Update of the list of accommodation units |  |  |  |
| 2(10) | - Short Survey at Destination: For the duration of 7 days in a month, 600 samples from the district to be collected at the destinations selected as per the 90% criteria. |  | Q4 | 15% |
| 2(11) | - Exit Survey: 14 days exercise in a month to perform the 400 surveys at the exit points. It is to be done at all the points of a district (railway stations, bus-stations, air-ports, and sea- Ports……) |  |  |  |
| 2(12) | - Accommodation Survey: All the classified Hotels and 10% of the units in each of the categories of other accommodation units. Information has to be Collected in the 1st week of every month for the preceding month. & Update of the list of accommodation units |  |  |  |
| 2(13) | - Approval of completion of work mentioned above from 2.1 to 2.12 by both State Government and MoT. |  | F&F | 10% |

*to be counted from the date of completion of deliverable at Sr. No. 4

## General conditions of the Contract (GCC)

### Relationship between the Parties:

Nothing contained herein shall be construed as establishing a relationship of master and servant or of principal and agent as between the Department and the Bidder. The Bidder, subject to this Contract, has complete charge of Personnel, if any, performing the Services and shall be fully responsible for the Services performed by them on his behalf. The Bidder will be exclusively liable to pay timely and remuneration and salary as per the statutory norms to his employees.

### Location:

The Services shall be performed at locations as mentioned in sub-clause (6) of clause 4.

### Taxes and Duties:

The Bidder shall be liable to pay all direct and indirect taxes, duties, fees and other impositions levied under the laws of India.

### Commencement, Completion, Modification and Termination of Contract:

      - Effectiveness of Contract: This Contract shall come into force and effect on the      date of signing of the Contract.

      - Termination of contract for Failure to become effective: If the Bidder does not submit Performance Guarantee after the date of the issue of work order.

      - Commencement of Services: The Bidder shall begin carrying out the Services immediately but not later than ten days from the Effective Date.

      - Completion of Contract: Unless terminated earlier pursuant to sub-clause (4) of clause 3 and sub-clause (4) of clause 8, the Bidder shall complete the entire work as per the time period stipulated in clause 7 of RFP.

      - Entire Agreement: This Contract contains all covenants, stipulations and provisions agreed by the Parties. No agent or representative of either Party has authority to make, and the Parties shall not be bound by or be liable for, any other statement, representation, promise or agreement not set forth herein.

- Force Majeure

- For the purposes of this Contract, “Force Majeure” means an event which is beyond the reasonable control of a Party, is not foreseeable, is unavoidable and not brought about by or at the instance of the Party claiming to be affected by such events and which has caused the non-performance or delay in performance, and which makes a Party’s performance of its obligations hereunder impossible or so impractical as reasonably to be considered impossible in the circumstances, and includes, but is not limited to, war, riots, civil disorder, earthquake, fire, explosion, storm, flood or other extreme adverse weather conditions, strikes, lockouts or other industrial action (except where such strikes, lockouts or other industrial action are within the power of the Party invoking Force Majeure to prevent), confiscation or any other action by Government agencies.

- Force Majeure shall not include

      - any event which is caused by the negligence or intentional action of a Party or by or of such Party’s agents or employees,

      - nor any event which a diligent Party could reasonably have been expected both to take into account at the time of the signing of the Contract, and avoid or overcome with utmost persistent effort in the carrying out of its obligations hereunder.

      - Force Majeure shall not include insufficiency of funds or manpower or inability to make any payment required for execution of services under this Contract.

- No Breach of Contract: The failure of a Party to fulfill any of its obligations hereunder shall not be considered to be a breach of, or default under, this Contract insofar as such inability arises from an event of Force Majeure, provided that the Party affected by such an event has taken all possible precautions, due care and all Measures, with the objective of carrying out the terms and conditions of this Contract.

### (d) Measures to be taken:

- A Party affected by an event of Force Majeure shall continue to perform its obligations under the Contract as far as is reasonably practical, and shall take all reasonable measures to minimize the consequences of any event of Force Majeure.

- A Party affected by an event of Force Majeure shall notify the other Party of such event as soon as possible, and in any case not later than fourteen (14) days following the occurrence of such event, providing sufficient and satisfactory evidence of the nature and cause of such event, and shall similarly give written notice of the restoration of normal conditions as soon  as possible.

- Any period within which a Party shall, pursuant to this Contract, complete any action or task, shall be extended for a period equal to the time during which such Party was unable to perform such action as a result of Force Majeure.

- During the period of their inability to perform the Services as a result of an event of Force Majeure, the Bidder, upon instructions by the Department shall either: (i) Demobilize or (ii) continue with the Services to the extent possible, in which case the Department, on being satisfied shall continue to pay proportionately to the Bidder and on prorate basis, under the terms of this Contract.

- In the case of disagreement between the Parties as to the existence or extent of Force Majeure, the matter shall be settled according to sub-clause (15) of clause 3 and sub-clause (1) of clause 14 hereunder.

### (6)     Withholding of payment:

      - The Department may, by written notice of suspension to the Bidder, suspend all payments to the Bidder hereunder if the Bidder fails to perform any of its obligations under this Contract, including the carrying out of the Services, provided that such notice of suspension (i) shall specify the nature of the failure, and (ii) shall allow the Bidder to remedy such failure, if capable of being remedied, within a period not exceeding thirty (30) days after receipt by the Bidder of such notice of suspension.

### (7)     Termination by the Department

- The Department may terminate this Contract in case of the occurrence of any of the events specified in entry (a) to (i) of this clause and sub-clause (4) of clause 3.

- if the Bidder fails to remedy a failure in the performance of its obligations hereunder, as specified in a notice issued by the Department, within thirty (30) days of receipt of such notice or within such further period as the Department, may have subsequently approved in writing;

(c)   if the Bidder or any of its Members which has substantial bearing on providing Services under this Contract becomes insolvent or goes into compulsory liquidation;

(d)   if the Bidder, in the judgment of the Department, has engaged in corrupt or fraudulent practices in competing for or in executing this Contract;

- if the Bidder submits to the Department, a false statement which has a material effect on the rights, obligations or interests of the Department;

- if the Bidder places itself in position of conflict of interest or fails to disclose promptly any conflict of interest to the Department;

- if, as the result of Force Majeure, the Bidder is unable to perform a material portion of the services for a period of not less than Sixty (60) days;

- if the Department, in its sole discretion and for any reason whatsoever, decides to terminate this Contract;

- in such an occurrence, the Department, shall give a not less than Thirty (30) days written advance notice before terminating the contract of bidders and Sixty (60) days in case of the event referred to in entry (g) and 100 (Hundred) days in case it does not pay the Awards amount as per Award against it passed by arbitration pursuant to sub-clause (1), (2) (3) of clause 15.

### Termination by the Bidder:

### (a) The Bidder may terminate this Contract, by not less than thirty (30) days’ written     notice to the  Department, subject to following conditions namely :-

- if the  Department, fails to pay any money due to the Bidder pursuant to this Contract and not subject to dispute pursuant to entry (h)  of sub-clause (7) of clause 8 within forty-five (45) days after receiving written notice from the Bidder that such payment is overdue;

- if, as the result of Force Majeure, the Bidder is unable to perform a material portion of the Services for a period of not less than sixty (60) days;

- if the Department fails to comply with any final decision reached as a result of Arbitration pursuant to sub clause (15) of clause 3 and sub clause (1) of clause 14 of this RFP;

- if the Department, is in material breach of its obligations pursuant to this Contract and has not remedied the same within forty-five (45) days (or such longer period as the Bidder may have subsequently approved in writing) following the receipt by Tourism and Civil Aviation Department, Govt. of Sikkim of the Bidder’s notice specifying such breach;

### Cessation of Rights and Obligations:

Upon termination of this Contract pursuant to sub-clause (4) of clause 3 hereof, or upon expiration of this Contract pursuant to sub-clause (4) of clause 8 thereof, all rights and obligations of the Parties hereunder shall cease, except (i) such rights and obligations as may have accrued on the date of termination or expiration, (ii) the obligation of confidentiality set forth in sub-clause (3) of clause 9 hereof, (iii) the Bidder’s obligation to pay Damages or Liquidated Damages permit inspection, copying and auditing of their accounts and records as set forth in clause 9 hereof, and (iv) any right which a Party may have under the Law.

### (10)   Cessation of Services:

Upon termination of this Contract by notice of either Party to the other pursuant to sub-clause (4) of clause 3 hereof, the Bidder shall, immediately upon dispatch or receipt of such notice, take all necessary steps to bring the Services to a close and vacate the premises of Tourism and Civil Aviation Department, Govt. of Sikkim  in  a prompt and orderly manner.

- Payment upon Termination:

Upon termination of this Contract pursuant to sub-clause (4) of clause 3 hereof, Tourism and Civil Aviation Department, Govt. of Sikkim  shall make the following        payments to the Bidder:

- If the agreement is terminated pursuant of sub-clause (4) of clause 3 the Bidder shall not be entitled to receive any agreed payments upon termination of the Contract. However, Tourism and Civil Aviation Department, Govt. of Sikkim  may consider making payment for the part satisfactorily performed on the basis of Quantum Merit as assessed by it, if such part is of economic utility to Tourism and Civil Aviation Department, Govt. of Sikkim subject to recovery of its dues, as permissible. Under such circumstances, upon termination, Tourism and Civil Aviation Department, Govt. of Sikkim may also impose liquidated damages as per the provisions of entry no. (i) of sub-clause (7) of clause 8 hereof. The Bidder will be required to pay any such liquidated damages and compensation as permissible under Contract Act to Tourism and Civil Aviation Department, Govt. of Sikkim within Thirty (30) days of termination date.

- In the event of termination under entry (a) to (e) of sub-clause (4) of clause 8, the payment schedule as specified in this contract shall not apply and the costs of work delivered by Bidder and the cost of demobilization of Bidder teams will be mutually settled between the Bidder and the Tourism and Civil Aviation Department, Govt. of Sikkim.

### (12)      Disputes about Events of Termination:

If either Party disputes whether an event specified in entry (a) to (e) of sub-clause (4) of clause 8 and sub-clause of (4) of clause 3 has occurred, such Party may, if it chosen within forty-five (45) days after receipt of notice of termination from the other Party, may seek settlement under sub-clause (11) of clause 8 thereof.

## OBLIGATIONS OF THE BIDDER

### General:

(1)  Standard of Performance: The Bidder shall perform the Services and carry out their obligations hereunder with all due diligence, efficiency and economy, in accordance with generally accepted professional standards and practices, and shall observe sound management practices, and employ appropriate technology and safe and effective equipment, machinery, materials and methods. The Bidder shall always act, in respect of any matter relating to this Contract or to the Services, as faithful adviser to Tourism and Civil Aviation Department, Govt. of Sikkim, and shall at all times support and safeguard Tourism and Civil Aviation Department, Govt. of Sikkim’s legitimate interests in any dealings with Third Parties.

### (2) Conflict of Interests:

The Bidder shall hold Tourism and Civil Aviation Department, Govt. of Sikkim’s interests paramount, without any consideration for future work, and strictly avoid conflict of interest with other assignments or their own corporate interests. If during the period of this Contract, a conflict of interest arises for any reasons, the Bidder shall promptly disclose the same to Tourism and Civil Aviation Department, Govt. of Sikkim and seek its instructions for compliance.

### Bidder not to benefit from Commissions, Discounts, etc.:

- The payment of the Bidder pursuant to entry (f) of sub-clause (7) of clause 8 hereof shall constitute the Bidder’s only payment in connection with this Contract. The Bidder shall not accept for its own benefit any trade commission, discount or similar payment in connection with activities pursuant to this Contract or in the discharge of its obligations hereunder, and the Bidder shall use its best efforts to ensure that any Personnel and agents of either of them, similarly shall not receive any such additional payment on account of commission or discount, etc.

- Furthermore, if the Bidder, as part of the Services, has the responsibility of advising the Department, on the procurement of goods, works or services, the Bidder shall comply with the Department, applicable procurement guidelines, and shall at all times exercise such responsibility in the best interest of the Department. Any discounts or commissions obtained by the Bidder in the exercise of such procurement responsibility shall be for the benefit and account of the Department.

### (b) Bidder and Affiliates Not to Engage in Certain Activities:

The Bidder agrees that, during the term of this Contract and after its termination, the Bidder and any entity affiliated with the Bidder, shall be disqualified from providing goods, works or services resulting from or directly related to the Bidder’s Services for the preparation or implementation of the project.

### (c) Prohibition of Conflicting Activities:

### The Bidder shall not engage, and shall cause their Personnel not to engage, either directly or indirectly, in any business or professional activities that would conflict with the activities assigned to them under this Contract.

### Confidentiality:

### Except with the prior written consent of the Department, the Bidder and the Personnel shall not at any time communicate to any person or entity any confidential information acquired in the course of the Services, nor shall the Bidder and its Personnel make public the recommendations formulated in the course of, award of Contract and its execution.

### Accounting:

The Bidder (i) shall keep accurate and systematic accounts and records in respect of the Services hereunder, in accordance with accounting principles and in such form and detail as will clearly identify all relevant time charges and costs, and (ii) if so required by the Department, shall undertake to provide such information as the Department, may reasonably determine as necessary in relation to the services.

- Bidder’s actions requiring the Department, prior approval:

The Bidder shall obtain the Department, prior approval in writing before taking any of the following actions:

- any change or addition to the Personnel listed in FORM TECH-4 of RFP;

- the Bidder shall not assign or transfer or subcontract the contract or any part thereof;

### Deliverables:

The Bidder shall submit to the Department, the reports and documents as specified in clause 7(1)  of the RFP  and within the time periods set forth in the said clause.

- Documents Prepared by the Bidder to be the Property the Department:

The Bidder may retain a copy of such documents, but shall not use anywhere, without taking permission, in writing, from Tourism and Civil Aviation Department, Govt. of Sikkim and Tourism and Civil Aviation Department, Govt. of Sikkim reserves right to grant or deny any such request.

## BIDDERS’ PERSONNEL

### General:

The Bidder shall employ and provide at its own cost such qualified and experienced Personnel as Surveyors, Supervisors etc. required to carry out the Services.

### Description of Personnel:

To be submitted by the Bidder as per the Formtech-4 of this RFP.

## 11.    Obligations of the Department

### (1) Assistance and Exemptions:

Unless otherwise specified, Tourism and Civil Aviation Department, Govt. of Sikkim shall use its best efforts to ensure that it shall:

- provide the Bidder including Personnel with work permits and such other documents as shall be necessary to enable the Bidder or Personnel to perform the Services;

- issue to officials, agents and representatives of the Government all such instructions as may be necessary or appropriate for the prompt and effective implementation of the Services;

- provide to the Bidder, Sub-Bidders and Personnel any such other assistance to facilitate performance of the Contract;

### (2) Payment:

In consideration of the Services performed by the Bidder under this Contract, the Department shall make to the Bidder such payments and in such manner as is provided by clause 7(2) of this      Contract.

### Office space and other facilities:

The Department shall provide office space for the Bidder’s personnel for the purpose of conducting discussions, meetings, and workshops with as mentioned in sub-clause (1) of clause 11 as and when required.

## PAYMENTS TO THE BIDDER

The payment to the Bidder will be made as per payment plan against the deliverables as per schedule of payments given in the table given under clause7(2)

              - Total Cost of the Services:

- the total cost of the Services payable is set forth in the contract agreement as per the Bidder’s proposal to the  Department and as negotiated thereafter;

- except as may be otherwise agreed under Clause 7(2)  and subject to payments under this Contract shall not exceed the amount specified in the contract;

### Currency of Payment:

All payments shall be made in Indian Rupees.

### Terms of Payment:

The payments in respect of the Services shall be made as follows; namely:-

- the Bidder shall submit the invoice for payment when the payment is due as per the agreed terms. The payment shall be released as per the work related milestones achieved;

- once a milestone is completed, the Bidder shall submit the requisite deliverables as specified in this Contract and such invoice (in triplicate) which falls due as per clause 7(2) titled “Schedule of Payment”. Tourism and Civil Aviation Department, Govt. of Sikkim shall release the requisite payment upon acceptance of the deliverables. However, if Tourism and Civil Aviation Department, Govt. of Sikkim fails to intimate acceptance of the deliverables or its objections thereto, within forty five (45) days of receipt of it, the  Department shall release the payment to the Bidder without further delay;

### Final Payment:

The final payment shall be made only after the final report and a final statement, identified as deliverable, shall have been submitted by the Bidder and approved by the Department. The Services shall be deemed completed and finally accepted by the Department and the final report and final statement shall be deemed approved by the Department as satisfactory after ninety (90) calendar days after receipt of the final report and final statement by the Department if within such ninety (90) day period, the Department, does not give written notice to the Bidder specifying in detail deficiencies in the Services specified, the final report or final statement. The Bidder shall thereupon promptly make all necessary corrections, and thereafter the foregoing process shall be repeated. Any extra amount, which the Department paid or caused to be paid in accordance with this Clause in excess of the amounts actually payable in accordance with the provisions of this Contract, shall be reimbursed by the Bidder to the Department within thirty (30) days after receipt by the Bidder of notice thereof. Any such claim by the Department for reimbursement must be made within two (2) calendar months after receipt by Bidder of a final report and a final statement approved by the Department in accordance with the above.

If the deliverables submitted by the Bidder are not acceptable to Tourism the Department reasons for such non-acceptance should be recorded in writing; the Department shall not release the payment due to the Bidder. This is without prejudice the Department right to levy any liquidated damages under sub-clause (9) of clause 8 and sub clause (1), (2) and (3) of clause 15. In such case, the payment will be released to the Bidder only after it resubmits the deliverable and which is accepted by the Department.

All payments under this Contract shall be made to the accounts of the Bidder.

The payment made to the Bidder do not constitute acceptance of the Services nor relieve the Bidder of any obligations hereunder, unless the acceptance has been communicated by the Department to the Bidder in writing and the Bidder has made necessary changes as per the comments / suggestions of the Department  communicated to the Bidder.

In case of earlier termination of the Contract, the payment shall be made to the Bidder as mentioned here with: (i) Assessment should be made about work done from the previous milestone, for which the payment is made or to be made till the date of the termination. The Bidder shall provide the details of persons reasonably worked during this period with supporting documents. The Department shall be entitled to adjust/ recover Damages/ Compensation and Liquidated Damages due under the Contract.

## FAIRNESS AND GOOD FAITH

### Good Faith:

The Parties undertake to act in good faith with respect to each other’s rights under this Contract and to adopt all reasonable measures to ensure the realization of the objectives of this Contract.

### Operation of the Contract:

The Parties recognize that it is impractical in this Contract to provide for every contingency which may arise during the life of the Contract, and the Parties hereby agree that it is their intention that this Contract shall operate fairly as between them, and without detriment to the interest of either of them, and that, if during the term of this Contract either Party believes that this Contract is operating unfairly, the Parties will make their best efforts to agree on such action as may be necessary to remove the cause or causes of such non-fairness, but no failure to agree on any action pursuant to this Clause may give rise to a dispute subject to Arbitration in accordance with Clause 15 hereof.

## Settlement of Disputes

### Amicable Settlement:

Performance of the Contract is governed by the terms and conditions of the Contract, in case of dispute arising between the Parties regarding any matter under the Contract, either Party of the Contract may send a written Notice of Dispute to the other Party in accordance to this clause. The Party receiving the Notice of Dispute will consider the Notice and respond to it in writing within Fifteen (15) days after receipt. If that Party fails to respond within Fifteen (15) days, or the dispute cannot be amicably settled within Forty-Five (45) days following the response of that Party, this clause shall become applicable.

- Arbitration: In the case of dispute arising upon or in relation to or in connection with the Contract between the Department and the Bidder, which has not been settled amicably, any Party can refer the dispute for Arbitration under (Indian) Arbitration and Conciliation Act, 1996. Such disputes shall be referred to the sole arbitrator to be appointed by the Department and the bidder on mutual consent and agreement.

- Arbitration proceedings shall be held in Gangtok (Sikkim) and the language of the Arbitration proceedings and that of all documents and communications between the Parties shall be English.

- The decision of the sole arbitrator shall be final and binding upon both Parties. The expenses of the arbitrators as determined by the arbitrators shall be shared equally by the Department and the Bidder. However, the expenses incurred by each Party in connection with the preparation, presentation shall be borne by the Party itself. All Arbitration awards shall be in writing and shall state the reasons for the award.

- Notwithstanding any references to arbitration, the parties shall continue to perform their respective work or obligation under the Contract.

## Penalty Clause:

- The Department reserves the right to deduct the penalty from pending bills submitted for the work already performed by the agency.

- The liquidated damages for delay by Bidder shall be applicable under following circumstances namely:-

- The amount of liquidated damages for delay by Bidder under this Contract shall not exceed 10 % (Ten Percent) of the total value of the Contract as specified in the contract agreement;

- Notwithstanding anything to the contrary contained in this agreement but subject to the indemnifications specifically agreed to by the Bidder herein, in no event shall the aggregate liability of the Bidder under this agreement exceed the total cost of services paid to the Bidder.

- If the services of the consultancy firm or bidder are found unsatisfactory and objectives of the study/survey are not fulfilled in spite of giving adequate opportunity to the bidder, Tourism and Civil Aviation Department, Govt. of Sikkim may withhold the payment amount due in part or whole sub-clause (6) of clause 8.

## Conflict of Interest

The Department policy requires that Bidders should provide professional, objective, and impartial advice and at all times hold the Department interests paramount; strictly avoid conflicts with other assignments or their own corporate   interests.

Without limitation on the generality of the foregoing, Bidders, and any of their affiliates, shall be considered to have a conflict of interest and shall not be engaged by the Department under any of the circumstances set forth below:

## Conflicting activities:

A firm that has been engaged by the Department to provide goods, works or services other than consulting services for a project, and any of its affiliates, shall be disqualified from providing consulting services related to those goods, works or services. Conversely, a firm hired to provide consulting services for the preparation or implementation of a project, and any of its affiliates, shall be disqualified from providing goods or works or services other than consulting services resulting from or directly related to the firm’s consulting services for such preparation or implementation. For the purpose of this paragraph, services other than consulting services are defined as those leading to a measurable physical output, for example surveys, exploratory drilling, aerial photography, and satellite imagery.

## Association of Sub-Bidders Bidder shall not assign or transfer the contract or any part thereof.

## Confidentiality:

Information relating to evaluation of Proposals and recommendations concerning awards shall not be disclosed to the Bidders who submitted the Proposals or to other persons not officially concerned with the process. The undue use by any Bidder of confidential information related to the process may result in the rejection of its Proposal and may be subject to the provisions of the Tourism and Civil Aviation Department, Govt. of Sikkim’s antifraud and corruption policy.

## Contract Price:

Contract price shall remain firm and fixed for the entire Contract period.

## Transfer of Contract:

Bidder shall not assign or transfer the contract or any part thereof.

## Time and Cost overrun due to pandemic:

There is a possibility of time overrun and consequent cost overrun in the work owing to the ongoing pandemic situation throughout the country. The Department shall not pay any additional cost other than quoted by the bidder. The bidder is solely responsible for bearing any cost overrun. The intermittent periods during which the work gets stopped due to ongoing Covid-19 pandemic situation shall not be counted in the time period of three years for which the manpower resource is to be deployed. However, bidder shall be at liberty to call back the manpower deployed during the intermittent periods in which the work gets stopped.

## Change Orders:

The Department may at any time, by a written order given to the bidder, make changes within the general scope of the Contract in any one or more of the following:

(a) the place of placement; or

(b) the Services to be provided by the Vendor.

- Tender Summary:

| S. No. | Particulars | Details |
| --- | --- | --- |
| 1 | Project Scope | Engagement of Survey Agencies for conducting Surveys for Data on Domestic and Foreign Tourist visitors/visits in Various Tourist Destinations/Accommodation Units/Entry-Exit Points in all districts of Sikkim |
| 2 | Contract Value | Rs. 25,00,000/- (Rupees Twenty Five Lakh) only |
| 3 | Contract Duration | 24 months from the date of Award of Work (Clause 5 of Section 6) |
| 4 | Validity of the Proposal | 30 days w.e.f date of publishing of RFP on website |
| 5 | Tender Fee | Bank Receipt of Rs. 5,000/- (Rupees Five thousand) only deposited with the State Bank of Sikkim towards the Cost of Tender Form (Non-Refundable) under receipt head 1452/TD, 800-Other receipts ‘OR’ Bank Challan in favour of Accounts Officer, Tourism & Civil Aviation Department, Government of Sikkim |
| 6 | Contact Person | Nodal Officer-cum-Assistant Director, MR & Statistics, Tourism & Civil Aviation Department, Government of Sikkim Contact No. +919635412368, 8617062811 |
| 7 | Performance Guarantee | 3% of the Contract Value |
| 8 | Documents to be submitted | Refer Clause 11 of Section 3, Clause 8(a) of Section 4, Annexure-E, Form Tech-1 to 5 & Annexure-2 |
| 9 | Relevant website/portal | www.sikkimtourism.gov.in |
| 10 | Bid Validity Period | 180 days (Refer Clause 12 of Section 3) |

Additional Secretary (ADM),

Tourism & Civil Aviation Department,

Government of Sikkim, Tadong,

Gangtok District, Sikkim

737102

Annexure – “A”

## List of Districts to be covered in Sikkim

- Mangan

- Gyalshing

- Namchi

- Gangtok

- Soreng

- Pakyong

## Annexure – “B”

## List of Destinations District wise

| Sl. No. | District | Name of Destination |
| --- | --- | --- |
| 1 | Mangan | - Yumthang - Gurudongmar - Phodong Monastry - Seven Sister’s Waterfalls - Dzongu - Kabi Lungchok |
| 2 | Gyalshing | - Statue of Chenrezig Singkham, Pelling - Pemayangste Monastry - Khechodpalri Lake - Yuksam - Rabdentse Ruins (Second Capital of Sikkim) - Kanchenjunga Waterfalls - Singshore Bridge - Statue of Srijunga Mangkhim, Bermiok - Tenzing Hillary Park, Uttarey |
| 3 | Namchi | - Siddheswara Dham, Solophok Namchi - Tathagata Tsal, Ravangla - Samdruptse, Namchi - Tareybhir, Sadam - Sirdi Sai Mandir, Namchi - Temi Tea Garden - Maenam Bhaleydunga - Pranami Mandir, Namphing - Phur-Cha-Chu Hot Spring, Legship |
| 4 | Gangtok | - Changu Lake - Nathula - Bakthang Falls - Tashi View Point, Gangtok - Ganesh Tok - Hanuman Tok - Rumtek Monastry - Namgyal Institute of Tibetology - Himalayan Zoological Park - Damodar Ropeway - Banjhakri Falls, Gangtok - Enchey Monsatry - Directorate of Handicrafts and Handloom, Zero Point Gangtok - Paruhang Sapten Mangkhim, Ranka |
| 5 | Soreng | - Daramdin Sai Mandir - Barsey Rhododendron Sanctuary - Rinchengpong - Sribadam Monastry - Azing Organic Farm, Sangadorji |
| 6 | Pakyong | - Zuluk (Old Silk Route) - Aritar Lampokhari - Karthok Monastry - Sidhi Vinayak Mandir, Rhenock - Yakten, Pakyong - Jhandidara |

## Annexure – “C”

## District wise List of Accommodation Units

Will be provided via e-mail.

## Annexure – “D”

## List of Exit points (Air/ Water/ Road/ Rail) District Wise)

| ## DISTRICT | ## CHECK POST | ## BUS STAND | ## TAXI STAND | ## AIRPORT |
| --- | --- | --- | --- | --- |
| ## Mangan | ## Kabi ## Dikchu ## Toong ## Sangkalang | ## Mangan ## Phodong ## Lachung ## Chungthang ## Hee Gyathang | ## Mangan ## Lachung ## Lachen ## Phodong ## Phensang ## Sangkalang ## Passingdang ## Hee Gyathang | ## N/A |
| ## Gyalshing | ## Legship ## Uttarey | ## Gyalshing ## Dentam | ## Gyalshing ## Dentam ## Yuksam ## Tashiding ## Uttarey ## Legship ## Darap | ## N/A |
| ## Namchi | ## Melli ## Mamring | ## Namchi ## Ravangla ## Jorethang ## Melli ## Namthang | ## Namchi ## Ravangla ## Jorethang ## Temi ## Kewzing ## Ralong ## Yangang ## Namthang ## Sadam | ## N/A |
| ## Gangtok | ## Ranipool ## 3rd Mile Check Post | ## SNT Bus Stand, Gangtok ## Private Bus Stand, Deorali ## Singtam | ## Deorali Private Stand ## South-West Taxi Stand, Deorali ## Children Park Stand ## Vajra Taxi Stand ## Ranipool | ## N/A |
| ## Soreng | ## Rammam ## Nayabazar | ## Soreng ## Sombaria | ## Soreng ## Nayabazar ## Sombaria ## Daramdin ## Reshi ## Mangalbaria ## Rinchengpong ## Sribadam | ## N/A |
| ## Pakyong | ## Rangpo ## Reshi | ## Rangpo ## Pakyong ## Rongli ## Rhenock | ## Rangpo ## Pakyong ## Rongli ## Rhenock | ## Green Field Airport, Pakyong |

## Annexure – “E”

## Cost and Work Load Estimation Sheet

| Sl. No. | Item |  | Reference Item No | Item = Details/ Unit/ Quantity/ Cost |
| --- | --- | --- | --- | --- |
| 1 | State code |  | (1) |  |
| 2 | State Name |  | (2) |  |
| 3 | No of Districts |  | (3) |  |
| 4 | Total No of listed Accommodation units |  | (4) |  |
| 5 | Total No of Tourist Exit Points (Bus Depot / Railway Station / Air Port / Sea Port) in the State common to Many or all Districts |  | (5) |  |
| 6 | No of Tourist Destinations | (a) Total | (6) |  |
| 7 |  | (b) Ticketed | (7) |  |
| 8 |  | (c) Non-Ticketed | (8) |  |
| 9 | Average number of Entry Points per Non-Ticketed Tourist Destinations |  | (9) |  |
| 10 | Average Duration of Normal Visiting Hours per Destination (hrs.) |  | (10) |  |
| 11 | Cost of Counting of Visitors per hour per Entry Point of the Non- Ticketed Destinations (in Rs.) |  | (11) |  |
| 12 | Estimated Total Cost of Counting for 14 days at Non-Ticketed Destinations in Phase-1 ( in Rs.) |  | (12) = (11) x (10) x (9) x (8) x 14 days |  |
| 13 | Cost of Collection of Records on Number of Tickets sold from a Ticketed destination (in Rs.) |  | (13) |  |
| 14 | Estimated Total Cost of Collection of Records on Number of Tickets sold for 14 days at Ticketed Destinations in Phase-1 (in Rs.) |  | (14) = (7) x (13) x 14 days |  |
| 15 | Cost of Flow study per day per Exit Point (in Rs.) |  | (15) |  |
| 16 | Estimated Cost of Flow study for 14 days at all Exit points of the State in Phase-1 (in Rs.) |  | (16) = (15) x (5) x 14 days |  |
| 17 | Average number of Ticketed destinations selected per district for Phase-2 study (using 90% criteria ) |  | (17) |  |
| 18 | Average number of Non-Ticketed destinations selected per district for Phase-2 study (using 90% criteria ) |  | (18) |  |
| 19 | Estimated Total Cost of Counting of Visitors at all entry points of the selected Non-ticketed destinations on prescribed 7-days of a month for 12‐months in Phase-2 ( in Rs. ) |  | (19) = (11) x (10) x (9) x 7 x 12 x (18) x (3) |  |
| 20 | Estimated Total Cost of Collection of Records on Number of Tickets sold from all selected Ticketed destinations on 14 prescribed days in a month continued for 12 months in Phase-2 (in Rs ) |  | (20) = (13) x (17) x 14 days |  |
| 21 | Cost of filling a destination-short- survey schedule (in Rs. ) |  | (21) |  |
| 22 | Estimated Total Cost of filling a total of 600 short survey schedules distributed over the selected destinations of a district and on 7 prescribed days in a month for 12 months at all districts of the state in Phase-2 (in Rs. ) |  | (22) = 600 x (21) x (3) x 12 |  |
| 23 | Cost of filling an Exit-survey Schedule (in Rs.) |  | (23) |  |
| 24 | Estimated Total Cost of filling a total of 400 Exit-Survey-Schedules distributed over all the exit points of the district and on 14 prescribed days in a month to be continued for 12 months in Phase- 2 (in Rs.) |  | (24) = 400 x (23) x (3) x12 |  |
| 25 | Cost of filling an Accommodation Census (Quarterly) schedule for obtaining requisite particulars from each listed accommodation unit in the state in Phase-2 (in Rs. ) |  | (25) |  |
| 26 | Estimated Total Cost of Accommodation Census (Quarterly updated) in phase-2 (in Rs.) |  | (26) = (25) x (4) x 4 |  |
| 27 | Cost of filling an Accommodation Monthly Survey schedule in Phase-2 (in Rs.) |  | (27) |  |
| 28 | Estimated Total Cost of Accommodation Survey (Month) in Phase-2 (in Rs.) |  | (28) = (27) x (4) |  |
| 29 | Average Number of Supervisors per District for Phase-1 and Phase‐2 both |  | (29) |  |
| 30 | Expected minimum Salary of a Supervisor per month during Phase-1 or 2 (in Rs.) |  | (30) |  |
| 31 | Estimated Total Salary of Supervisors (Phase-1 of 1 month and Phase-2 of 12 months) (in Rs. ) |  | (31) = (30) x (29) x (3) x13 months |  |
| 32 | Estimated Total Travelling Cost |  | (32) |  |
| 33 | Estimated Total Administrative Cost |  | (33) |  |
| 34 | Estimated Total Miscellaneous Cost |  | (34) |  |
| 35 | Estimated Total Incidentals |  | (35) |  |
| 36 | Estimated Total Cost (in Rs.) |  | (36) = (12) + (16) + (19) + (20) + (22) + (24) + (26) + (28) + (31) + (32) + (33) + (34) + (35) |  |
| 37 | Amount in Words (INR Only) |  |  |  |

## Form Tech-1

# Financial Bid Form

| Description | Cost per Man-day (Rs./ Man-Day) |
| --- | --- |
| The Man-day cost for conducting the activities detailed in the RFP is required to be provided here. |  |
| Amount in Words (INR Only) |  |
| - The man-day cost is to be arrived at by considering Remuneration of key personnel, expenses on transportation, accommodation, TA/DA, local transportation, online methods, training & analysis tools/software application etc. Also include, miscellaneous Expenses related to assignment such as office expenses, documentation, communication, data entry, data analysis etc. salary, TA/DA, - Also consider applicable taxes |  |

## M/s…	hereby submits the Financial Bid to

Undertake the activities mentioned in the RFP No……………………………………

## dated………………….at the rate of Rs	per man-day.

Total Financial Bid Amount = Rs. _____________/- (Rupees ___________________)

### Date:

Place:

### SIGNATURE

Full name and Designation:

(Seal of Agency)

FORM TECH– 2

## DECLARATION (ON THE LETTER HEAD OF THE BIDDER)

### To,

The Nodal Officer-cum-Deputy Director,

### Tourism and Civil Aviation Department,

### Government of Sikkim,

Tadong, Gangtok- 737102

Dear Sir,

We, the undersigned offer to provide services for conducting the tourism survey at Destination, District level & State Level and Engagement in accordance with the RFP No ....................................... dated ___________ issued by Tourism and Civil Aviation Department, Government of Sikkim. We are hereby submitting our Financial bid as per Form tech‐1 for Tourism and Civil Aviation Department, Government of Sikkim.

We hereby declare that all the information and statements made in this bid are true and accept that any misinterpretation contained in it may lead to disqualification of our bid.

- We understand that you are not bound to accept any proposal you receive.

- We permit Tourism and Civil Aviation Department, Government of Sikkim to cross check the facts from any other source.

- We or any of our authorized representatives, if required by Tourism and Civil Aviation Department, Government of Sikkim would make a presentation before the duly constituted Committee at our own cost.

- We will abide by the decision of Tourism and Civil Aviation Department, Government of Sikkim regarding engagement bid process& thereafter.

- We have read & understood the RFP and agree to all the terms & conditions          stated therein.

### Date:

Place:

### SIGNATURE

### Full Name and Designation

### (Seal of Agency)

## FORM TECH – 3

## Bid Security Declaration Form

Date:……………………………….. RFP No.,…………………………………………..

To,

### Tourism and Civil Aviation Department,

### Government of  Sikkim,

Tadong, Gangtok- 737102

I/We, The undersigned, declare that:

I/We understand that, according to your conditions, bids must be supported by a Bid Securing Declaration.

I/We accept that I/We may be disqualified from bidding for any contract with you for a period of one year from the date of notification if I am /We are in a breach of any obligation under the bid conditions, because I/We:

- have withdrawn/modified/amended, impairs or derogates from the tender, my/our Bid during the period of bid validity specified in the form of Bid; or

- Having been notified of the acceptance of our Bid by the purchaser during the period of bid validity (i) fail or (ii) refuse to execute the contract in accordance with the Instructions to Bidders.

I/We understand this Bid Security Declaration shall cease to be valid if I am/we are not the successful Bidder, upon the earlier of (i) the receipt of your notification of the name of the successful Bidder; or (ii) thirty days after the expiration of the validity of my/our Bid.

Signed:	(insert signature of person whose name and capacity

are shown) in the capacity of (insert legal capacity of person signing the Bid Securing  Declaration)

Name:	(insert complete name of person signing

the Bid Securing Declaration) Duly authorized to sign the bid for an on behalf of

…………………………………………… (insert complete name of Bidder)

Dated on	day of	(insert date of signing)  Corporate Seal (where appropriate)

Note: In case of a Joint Venture, the Bid Securing Declaration must be in the name of all partners to the Joint Venture that submits the bid)

# FORM TECH – 4

## List of Surveyors

| Name | Qualification | Years of Experience | Engagement Full Time/ Part Time | Languages known | Availability of Tab/ Smart phone |
| --- | --- | --- | --- | --- | --- |

Consent of the Agency: I hereby declare that all the information mentioned above is true and correct to the best of my knowledge and belief.

### (Name & Signature of the Authorized Signatory)

Date:

### Place:	Authorized Signatory

Name:

AGENCY SEAL

# Form tech-5

## Banking Details Proforma of the Bidder

### Please note that the applicable amount is to be paid only through NEFT/RTGS. The bank details are as follows:

Bank Account No.	:

Type of Account [CA/SB/Loan/CC]:

Name of the Bank	:

Branch	:

Address	:

City	:

IFSC RTGS Code	:

IFSC NEFT Code	:

MICR Code                                   :

Branch Code	:

Please note that <<M/S Bidders Name>> PAN Number:

<<M/S Bidders Name>> Service Tax Regn. No.:

<<M/S Bidders Name>> TIN No.:

<<M/S Bidders Name>> TAN No.:

<<M/S Bidders Name>> Provisional GST ID No.:

GST Form-Application for registration of existing taxpayer has been filed by <<M/S Bidders Name>> against Application Registration Number (ARN):

## ANNEXURE -1

# Tourism Survey Methodology

Will be provided via e-mail

ANNEXURE – 2

GOVERNMENT OF SIKKIM

TOURISM & CIVIL AVIATION DEPARTMENT

- PARYATAN BHAWAN

- TADONG, EAST SIKKIM

- TENDER/BID FORM

Bank Receipt/Challan No. __________                                                      Date: _____________

- Name of the Bidder/Agency                   _______________________________________

- Address of Head Office :                        _______________________________________

(with complete postal address)              _______________________________________

_______________________________________

- Address of Branch Office :                      _______________________________________

(with complete postal address)              _______________________________________

- Contact No. :                                           _______________________________________

- Amount of Bid :                                      _______________________________________

(Rupees _______________________________

- Enclosures:                                           (a) Bank Receipt of Rs. 5000/- (Rupees Five         						                 Thousand) only (Non-Refundable) duly credited 						                  under Budget Head – 1452/TD ‘OR’ Banker’s 							      Cheque.

(b) TDR/Demand Draft from any Nationalized  Bank of Rupees 5,000/- (Non-refundable) payable to Secretary  Tourism & Civil Aviation Department, Government of  Sikkim.

Certified that the above information is true to the best of my/our knowledge and belief. I/We will not bring or attempt to bring any political or outside influence to bear upon any superior authority to further my/our interest in respect of matters pertaining to this tender. Further, I/We assure the Department that I/We will not assign or sublet or otherwise part with possession of the premises or any part of the assignment thereof.

Signature of Bidder (with Seal)